## Aug 19
Statewise status of Survey of Manual Scavengers as on20.8.2019
S.No. | State | Districts Identified for Survey | Survey Reports Received | Nil Identification Survey Reported | Survey Report Awaited | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of Survey Forms received | No. of forms digitised | No. of MS Released OTCA
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |  | (9) | (10) | (11)
1 | Andhra Pradesh | 5 | 5 | 2 | 0 | 2024 | 1982 | 1963 | 1963 | 1562 | 1404
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 542 | 542 | 542 | 538
3 | Bihar | 16 | 16 | 16 | 0 | 4757 | 0
4 | Gujarat | 4 | 4 | 1 | 0 | 291 | 108 | 108 | 108 | 108 | 96
5 | Haryana | 5 | 5 | 5 | 0 | 1221 | 0
6 | J & K | 7 | 7 | 7 | 0 | 254 | 0
7 | Jharkhand | 3 | 3 | 1 | 0 | 246 | 201 | 199 | 199 | 131 | 108
8 | Karnataka | 6 | 6 | 0 | 0 | 1803 | 1754 | 1728 | 1728 | 1265 | 956
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 598 | 598 | 543 | 504
10 | Madhya Pradesh | 14 | 14 | 7 | 0 | 8572 | 562 | 518 | 518 | 386 | 305
11 | Maharashtra | 14 | 14 | 0 | 0 | 7378 | 7378 | 7250 | 7250 | 6754 | 5484
12 | Punjab | 4 | 4 | 2 | 0 | 636 | 142 | 142 | 142 | 142 | 125
13 | Rajasthan | 20 | 20 | 12 | 0 | 7381 | 2590 | 2525 | 2525 | 2463 | 2037
14 | Tamil Nadu | 6 | 6 | 3 | 0 | 1433 | 62 | 58 | 58 | 47 | 41
15 | Telangana | 2 | 2 | 2 | 0 | 288 | 0
16 | Uttar Pradesh | 47 | 47 | 23 | 0 | 41068 | 19712 | 16934 | 16934 | 15008 | 9189
17 | Uttarakhand | 4 | 4 | 1 | 0 | 7440 | 6033 | 4766 | 4766 | 2421 | 1755
18 | West Bengal | 6 | 6 | 2 | 0 | 1329 | 637 | 633 | 633 | 627 | 559
| Total | 170 | 170 | 84 | 0 | 87913 | 42303 | 37964 | 37964 | 31999 | 23101

## Jul 19
Statewise status of Survey of Manual Scavengers as on 31.7.2019
S.No. | State | Districts Identified for Survey | Survey Reports Received | Nil Identification Survey Reported | Survey Report Awaited | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of Survey Forms received | No. of forms digitised | No. of MS Released OTCA
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |  | (9) | (10) | (11)
1 | Andhra Pradesh | 5 | 5 | 2 | 0 | 2024 | 1982 | 1963 | 1963 | 1562 | 1404
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 542 | 542 | 542 | 538
3 | Bihar | 16 | 16 | 16 | 0 | 4757 | 0
4 | Gujarat | 4 | 4 | 1 | 0 | 291 | 108 | 108 | 108 | 108 | 96
5 | Haryana | 5 | 5 | 5 | 0 | 1221 | 0
6 | J & K | 7 | 7 | 7 | 0 | 254 | 0
7 | Jharkhand | 3 | 3 | 1 | 0 | 246 | 201 | 199 | 199 | 131 | 108
8 | Karnataka | 6 | 6 | 0 | 0 | 1803 | 1754 | 1728 | 1728 | 1265 | 956
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 598 | 598 | 543 | 504
10 | Madhya Pradesh | 14 | 14 | 7 | 0 | 8572 | 562 | 518 | 518 | 386 | 305
11 | Maharashtra | 14 | 14 | 0 | 0 | 7378 | 7378 | 7250 | 7250 | 6754 | 5484
12 | Punjab | 4 | 4 | 2 | 0 | 636 | 142 | 142 | 142 | 142 | 125
13 | Rajasthan | 20 | 20 | 12 | 0 | 7381 | 2590 | 2525 | 2525 | 2463 | 2037
14 | Tamil Nadu | 6 | 6 | 3 | 0 | 1433 | 62 | 58 | 58 | 47 | 41
15 | Telangana | 2 | 2 | 2 | 0 | 288 | 0
16 | Uttar Pradesh | 47 | 43 | 21 | 4 | 39683 | 18529 | 16934 | 16934 | 15008 | 9189
17 | Uttarakhand | 4 | 4 | 1 | 0 | 7440 | 6033 | 4766 | 4766 | 2421 | 1755
18 | West Bengal | 6 | 6 | 2 | 0 | 1329 | 637 | 633 | 633 | 627 | 559
| Total | 170 | 166 | 82 | 4 | 86528 | 41120 | 37964 | 37964 | 31999 | 23101

## Jun 19
Statewise status of Survey of Manual Scavengers as on 30.6.2019
S.No. | State | Districts Identified for Survey | Survey Reports Received | Nil Identification Survey Reported | Survey Report Awaited | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of Survey Forms received | No. of forms digitised | No. of MS Released OTCA
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |  | (9) | (10) | (11)
1 | Andhra Pradesh | 5 | 5 | 2 | 0 | 2024 | 1982 | 1963 | 1963 | 1562 | 1404
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 542 | 542 | 542 | 538
3 | Bihar | 16 | 16 | 16 | 0 | 4757 | 0
4 | Gujarat | 4 | 4 | 1 | 0 | 291 | 108 | 108 | 108 | 108 | 96
5 | Haryana | 5 | 5 | 5 | 0 | 1221 | 0
6 | J & K | 7 | 7 | 7 | 0 | 254 | 0
7 | Jharkhand | 3 | 3 | 1 | 0 | 246 | 201 | 199 | 199 | 131 | 108
8 | Karnataka | 6 | 6 | 0 | 0 | 1803 | 1754 | 1728 | 1728 | 1265 | 871
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 598 | 598 | 543 | 504
10 | Madhya Pradesh | 14 | 14 | 7 | 0 | 8572 | 562 | 518 | 518 | 386 | 305
11 | Maharashtra | 14 | 14 | 0 | 0 | 7298 | 7298 | 7250 | 7250 | 6754 | 5484
12 | Punjab | 4 | 4 | 2 | 0 | 636 | 142 | 142 | 142 | 142 | 125
13 | Rajasthan | 20 | 20 | 12 | 0 | 7381 | 2590 | 2525 | 2525 | 2463 | 2037
14 | Tamil Nadu | 6 | 6 | 3 | 0 | 1433 | 62 | 58 | 58 | 47 | 41
15 | Telangana | 2 | 2 | 2 | 0 | 288 | 0
16 | Uttar Pradesh | 47 | 37 | 19 | 10 | 35093 | 17828 | 16833 | 16833 | 14584 | 5458
17 | Uttarakhand | 4 | 3 | 1 | 1 | 6194 | 4787 | 4766 | 4766 | 2421 | 1755
18 | West Bengal | 6 | 6 | 2 | 0 | 1329 | 637 | 633 | 633 | 627 | 559
| Total | 170 | 159 | 80 | 11 | 80612 | 39093 | 37863 | 37863 | 31575 | 19285

## May 19
Statewise status of Survey of Manual Scavengers as on 31.5.2019
S.No. | State | Districts Identified for Survey | Survey Reports Received | Nil Identification Survey Reported | Survey Report Awaited | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of Survey Forms received | No. of forms digitised | No. of MS Released OTCA
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |  | (9) | (10) | (11)
1 | Andhra Pradesh | 5 | 5 | 2 | 0 | 2024 | 1982 | 1963 | 1963 | 1562 | 1333
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 542 | 542 | 542 | 538
3 | Bihar | 16 | 16 | 16 | 0 | 4757 | 0
4 | Gujarat | 4 | 4 | 1 | 0 | 291 | 108 | 108 | 108 | 108 | 96
5 | Haryana | 5 | 5 | 5 | 0 | 1221 | 0
6 | J & K | 7 | 7 | 7 | 0 | 254 | 0
7 | Jharkhand | 3 | 3 | 1 | 0 | 246 | 201 | 199 | 199 | 131 | 108
8 | Karnataka | 6 | 6 | 0 | 0 | 1803 | 1754 | 1728 | 1728 | 1265 | 818
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 598 | 598 | 543 | 504
10 | Madhya Pradesh | 14 | 14 | 7 | 0 | 8572 | 562 | 518 | 518 | 386 | 305
11 | Maharashtra | 14 | 14 | 0 | 0 | 7298 | 7298 | 7250 | 7250 | 6495 | 4605
12 | Punjab | 4 | 4 | 2 | 0 | 636 | 142 | 142 | 142 | 142 | 125
13 | Rajasthan | 20 | 20 | 12 | 0 | 7381 | 2590 | 2525 | 2525 | 2463 | 2037
14 | Tamil Nadu | 6 | 6 | 3 | 0 | 1433 | 62 | 58 | 58 | 47 | 34
15 | Telangana | 2 | 2 | 2 | 0 | 288 | 0
16 | Uttar Pradesh | 47 | 36 | 18 | 11 | 34041 | 17828 | 16833 | 16833 | 14134 | 4968
17 | Uttarakhand | 4 | 3 | 1 | 1 | 6194 | 4787 | 4766 | 4766 | 2414 | 1755
18 | West Bengal | 6 | 6 | 2 | 0 | 1329 | 637 | 633 | 633 | 627 | 555
| Total | 170 | 158 | 79 | 12 | 79560 | 39093 | 37863 | 37863 | 30859 | 17781

## April 19
Statewise status of Survey of Manual Scavengers as on 30.4.2019
S.No. | State | Districts Identified for Survey | Survey Reports Received | Nil Identification Survey Reported | Survey Report Awaited | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of Survey Forms received | No. of forms digitised | No. of MS Released OTCA
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |  | (9) | (10) | (11)
1 | Andhra Pradesh | 5 | 5 | 2 | 0 | 2024 | 1982 | 1960 | 1963 | 1562 | 1333
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 542 | 542 | 542 | 538
3 | Bihar | 16 | 16 | 16 | 0 | 4757 | 0
4 | Gujarat | 4 | 4 | 1 | 0 | 291 | 108 | 108 | 108 | 108 | 96
5 | Haryana | 5 | 5 | 5 | 0 | 1221 | 0
6 | J & K | 7 | 7 | 7 | 0 | 254 | 0
7 | Jharkhand | 3 | 3 | 1 | 0 | 246 | 201 | 199 | 199 | 131 | 108
8 | Karnataka | 6 | 6 | 0 | 0 | 1791 | 1742 | 1713 | 1716 | 1265 | 818
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 598 | 598 | 543 | 504
10 | Madhya Pradesh | 14 | 14 | 7 | 0 | 8572 | 562 | 1095 | 518 | 386 | 305
11 | Maharashtra | 14 | 14 | 0 | 0 | 6387 | 6387 | 6378 | 6319 | 5842 | 4605
12 | Punjab | 4 | 4 | 2 | 0 | 636 | 142 | 142 | 142 | 142 | 125
13 | Rajasthan | 20 | 20 | 12 | 0 | 7381 | 2590 | 2531 | 2525 | 2463 | 2037
14 | Tamil Nadu | 6 | 6 | 3 | 0 | 1433 | 62 | 58 | 58 | 47 | 34
15 | Telangana | 2 | 2 | 2 | 0 | 288 | 0
16 | Uttar Pradesh | 47 | 31 | 14 | 16 | 31995 | 16663 | 12789 | 15668 | 13832 | 4968
17 | Uttarakhand | 4 | 2 | 1 | 2 | 3084 | 2531 | 2517 | 2518 | 2288 | 1755
18 | West Bengal | 6 | 6 | 2 | 0 | 1329 | 637 | 632 | 633 | 627 | 555
| Total | 170 | 152 | 75 | 18 | 73481 | 34749 | 31262 | 33507 | 29778 | 17781

## Mar 19
Statewise status of Survey of Manual Scavengers as on 31.3.2019
S.No. | State | Districts Identified for Survey | Survey Reports Received | Nil Identification Survey Reported | Survey Report Awaited | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of Survey Forms received | No. of forms digitised | No. of MS Released OTCA
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |  | (9) | (10) | (11)
1 | Andhra Pradesh | 5 | 5 | 2 | 0 | 2024 | 1982 | 1960 | 1963 | 1562 | 1333
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 542 | 542 | 542 | 538
3 | Bihar | 16 | 16 | 16 | 0 | 4757 | 0
4 | Gujarat | 4 | 4 | 1 | 0 | 291 | 108 | 108 | 108 | 108 | 96
5 | Haryana | 5 | 5 | 5 | 0 | 1221 | 0
6 | J & K | 7 | 7 | 7 | 0 | 254 | 0
7 | Jharkhand | 3 | 3 | 1 | 0 | 246 | 201 | 199 | 199 | 131 | 108
8 | Karnataka | 6 | 6 | 0 | 0 | 1791 | 1742 | 1713 | 1716 | 1265 | 818
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 598 | 598 | 543 | 504
10 | Madhya Pradesh | 14 | 14 | 7 | 0 | 8572 | 562 | 1095 | 518 | 386 | 305
11 | Maharashtra | 14 | 14 | 0 | 0 | 6387 | 6387 | 6378 | 6323 | 5842 | 4605
12 | Punjab | 4 | 4 | 2 | 0 | 636 | 142 | 142 | 142 | 142 | 125
13 | Rajasthan | 20 | 20 | 12 | 0 | 7381 | 2590 | 2531 | 2525 | 2463 | 2037
14 | Tamil Nadu | 6 | 6 | 3 | 0 | 1433 | 62 | 58 | 58 | 47 | 34
15 | Telangana | 2 | 2 | 2 | 0 | 288 | 0
16 | Uttar Pradesh | 47 | 31 | 14 | 16 | 31995 | 16663 | 12789 | 15668 | 11897 | 4968
17 | Uttarakhand | 4 | 2 | 1 | 2 | 3084 | 2531 | 2517 | 2518 | 2288 | 1755
18 | West Bengal | 6 | 6 | 2 | 0 | 1329 | 637 | 632 | 633 | 627 | 555
| Total | 170 | 152 | 75 | 18 | 73481 | 34749 | 31262 | 33511 | 27843 | 17781

## Feb 19
Statewise status of Survey of Manual Scavengers as on 28.2.2019
S.No. | State | Districts Identified for Survey | Survey Reports Received | Nil Identification Survey Reported | Survey Report Awaited | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of Survey Forms received | No. of forms digitised | No. of MS Released OTCA
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |  | (9) | (10) | (11)
1 | Andhra Pradesh | 5 | 4 | 1 | 1 | 2024 | 1982 | 1960 | 1960 | 1562 | 1333
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 542 | 542 | 542 | 538
3 | Bihar | 16 | 16 | 16 | 0 | 4757 | 0
4 | Gujarat | 4 | 4 | 1 | 0 | 291 | 108 | 108 | 108 | 108 | 93
5 | Haryana | 5 | 5 | 5 | 0 | 1221 | 0
6 | J & K | 7 | 7 | 7 | 0 | 254 | 0
7 | Jharkhand | 3 | 2 | 0 | 1 | 246 | 201 | 199 | 199 | 131 | 108
8 | Karnataka | 6 | 6 | 0 | 0 | 1791 | 1742 | 1713 | 1713 | 1265
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 598 | 598 | 543 | 488
10 | Madhya Pradesh | 14 | 14 | 7 | 0 | 8572 | 562 | 1095 | 1095 | 820 | 113
11 | Maharashtra | 14 | 14 | 0 | 0 | 6387 | 6387 | 6378 | 6378 | 5842 | 3928
12 | Punjab | 4 | 4 | 2 | 0 | 636 | 142 | 142 | 142 | 142 | 125
13 | Rajasthan | 20 | 20 | 12 | 0 | 7381 | 2590 | 2531 | 2531 | 2461 | 2037
14 | Tamil Nadu | 6 | 6 | 3 | 0 | 1433 | 62 | 58 | 58 | 47 | 34
15 | Telangana | 2 | 2 | 2 | 0 | 288 | 0
16 | Uttar Pradesh | 47 | 23 | 10 | 24 | 28043 | 13801 | 12789 | 12789 | 9940 | 4968
17 | Uttarakhand | 4 | 2 | 1 | 2 | 3084 | 2531 | 2517 | 2517 | 2288 | 1755
18 | West Bengal | 6 | 6 | 2 | 0 | 1329 | 637 | 632 | 632 | 627 | 555
| Total | 170 | 142 | 69 | 28 | 69529 | 31887 | 31262 | 31262 | 26318 | 16075

## Jan 19
Statewise status of Survey of Manual Scavengers as on 24.1.2019
S.No. | State | Districts Identified for Survey | Survey Reports Received | Nil Identification Survey Reported | Survey Report Awaited | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of Survey Forms received | No. of forms digitised | No. of MS Released OTCA
1 | Andhra Pradesh | 5 | 4 | 1 | 1 | 2024 | 1982 | 1. Camp not Scheduled in Anantpur Distt. 2. Distt. Coordinators not involved in survey except in Krishna Distt. 3. Survey Reports alongwith minutes and completed survey forms not received from Districts except minutes received from Krishna Distt. | 1982 | 1545 | 1333
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 1. Survey Report with minutes received from Distt. Golaghat. Survey forms yet to be received. 2. Survey reports and forms yet to be received from other two districts viz. Jorhat and Lakhimpur. | 542 | 542 | 510
3 | Bihar | 16 | 16 | 16 | 0 | 4757 | 0 | 1. Survey camps yet to be scheduled in Araria, Aurangabad, Baxur, Gopalganj, Jahanabad, Katihar, Nalanda, Rohtas, Saharsa and Supaul 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately.
4 | Gujarat | 4 | 4 | 1 | 0 | 291 | 108 | 1. Survey report with 126 forms received from Ahmedabad and Rajkot Distts. Minutes of the Survey Camps not received. Survey forms are not signed by Nodal Oficer and Distt. Coordinators and not filled fully. 2. For Surendra Nagar Only Survey Report of identication of 20 MS received. No minutes or survey forms received. 3. In Distt. Anand no MS identified. 4. Distts. Anand and Surendra Nagar were added in the list of survey districts at the request of SKA. Perhaps Distt. Coord. were not actively involved in the survey in these districts. | 108 | 108 | 93
5 | Haryana | 5 | 5 | 5 | 0 | 1221 | 0 | 1. Information about holding of survey camp in Karnal not received. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately.
6 | J & K | 7 | 0 |  | 7 |  |  | No Survey camps scheduled so far.
7 | Jharkhand | 3 | 2 | 0 | 1 | 246 | 201 | No Survey camps scheduled so far. | 201 | 131 | 108
8 | Karnataka | 6 | 6 | 0 | 0 | 1791 | 1742 | No Survey camps scheduled so far. | 1719 | 1192
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 1. Complete Survey Reports and forms duly translated in English received from Ernakulam and Pallakad Districts. 2. Alapuza Distt. Sent only minutes of the survey camps. | 598 | 543 | 488
10 | Madhya Pradesh | 14 | 14 | 6 | 0 | 8572 | 1133 | 1. Survey camps yet to be scheduled in Anupur, Ashoknagar, Katni, Narsingpur, Panna and Satna. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 1095 | 564 | 113
11 | Maharashtra | 14 | 14 | 0 | 0 | 6387 | 6387 | 1. Survey completed in all 14 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 6378 | 5018 | 3594
12 | Punjab | 4 | 4 | 2 | 0 | 636 | 142 | 1. Survey Camps yet to be scheduled in Ludhiana. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 142 | 138 | 125
13 | Rajasthan | 20 | 20 | 12 | 0 | 7381 | 2590 | 1. Survey completed in all 20 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Distt. Coordinator not involved in survey by Jaipur Municipal Corporation. | 2531 | 2445 | 2037
14 | Tamil Nadu | 6 | 6 | 3 | 0 | 1433 | 62 | Survey completed in all 6 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 58 | 40 | 34
15 | Telangana | 2 | 2 | 2 | 0 | 288 | 0 | No detail of Survey camps scheduled so far involving Distt. Coordinators.
16 | Uttar Pradesh | 47 | 13 | 4 | 34 | 24967 | 11608 | 1. Survey camps yet to be scheduled in districts Banda, Barabanki, Hamirpur, Jaunpur and Kaushambi. 2. Survey partly scheduled in Lucknow, Meerut, Muzafarnagar and Saharanpur in urban areas only. 3. Survey reports alongwith survey forms yet to be received from all the districts. 4. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 11611 | 8573 | 4968
17 | Uttarakhand | 4 | 2 | 1 | 2 | 3084 | 2531 | Survey reports alongwith survey forms yet to be received from all the districts. | 2517 | 2287 | 1755
18 | West Bengal | 6 | 6 | 2 | 0 | 1329 | 637 | No Survey camps scheduled so far. | 637 | 622 | 555
| Total | 170 | 125 | 55 | 45 | 66199 | 30265 | 0 | 30119 | 23748 | 15713

## DEc 18
Statewise status of Survey of Manual Scavengers as on 31.12.18
S.No. | State | Districts Identified for Survey | Where Survey Camps completed | Where Survey camps underway | Where Survey camps not scheduled | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of MS Identified before this Survey | Total No. of MS Identified in both Surveys | No. of Survey Forms received | No. of forms digitised | No. of MS OTCA |  |  | Remarks
[13 empty] | Released | Rejected | Confirmed
1 | Andhra Pradesh | 5 | 5 | 0 | 0 | 2024 | 1982 | 1. Camp not Scheduled in Anantpur Distt. 2. Distt. Coordinators not involved in survey except in Krishna Distt. 3. Survey Reports alongwith minutes and completed survey forms not received from Districts except minutes received from Krishna Distt. | 78 | 2060 | 1721 | 1545 | 1333 |  | 1333 | Anantpur & Krishna Distt. Forms received
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 1. Survey Report with minutes received from Distt. Golaghat. Survey forms yet to be received. 2. Survey reports and forms yet to be received from other two districts viz. Jorhat and Lakhimpur. | 154 | 696 | 542 | 542 | 510 | 1 | 509
3 | Bihar | 16 | 16 | 0 | 0 | 846 | 0 | 1. Survey camps yet to be scheduled in Araria, Aurangabad, Baxur, Gopalganj, Jahanabad, Katihar, Nalanda, Rohtas, Saharsa and Supaul 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 137 | 137 |  |  |  |  | 0 | Araria Distt. Report received.
4 | Gujarat | 4 | 4 | 0 | 0 | 291 | 108 | 1. Survey report with 126 forms received from Ahmedabad and Rajkot Distts. Minutes of the Survey Camps not received. Survey forms are not signed by Nodal Oficer and Distt. Coordinators and not filled fully. 2. For Surendra Nagar Only Survey Report of identication of 20 MS received. No minutes or survey forms received. 3. In Distt. Anand no MS identified. 4. Distts. Anand and Surendra Nagar were added in the list of survey districts at the request of SKA. Perhaps Distt. Coord. were not actively involved in the survey in these districts. | 0 | 108 | 108 | 108 | 93 |  | 93
5 | Haryana | 5 | 5 | 0 | 0 | 1221 | 0 | 1. Information about holding of survey camp in Karnal not received. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 0 | 0 | 0 |  |  |  | 0 | No MS identified in State. State Govt. requested to review.
6 | J & K | 7 | 0 | 0 | 7 |  |  | No Survey camps scheduled so far. | 0 | 0 |  |  |  |  | 0
7 | Jharkhand | 3 | 3 | 0 | 0 | 246 | 201 | No Survey camps scheduled so far. | 0 | 201 | 201 | 131 | 108 |  | 108
8 | Karnataka | 6 | 6 | 0 | 0 | 1793 | 1744 | No Survey camps scheduled so far. | 732 | 2476 | 1719 | 1192 |  |  | 0
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 1. Complete Survey Reports and forms duly translated in English received from Ernakulam and Pallakad Districts. 2. Alapuza Distt. Sent only minutes of the survey camps. | 0 | 600 | 598 | 543 | 488 | 5 | 483
10 | Madhya Pradesh | 14 | 14 | 0 | 0 | 8275 | 1447 | 1. Survey camps yet to be scheduled in Anupur, Ashoknagar, Katni, Narsingpur, Panna and Satna. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 36 | 1483 | 992 | 564 | 113 |  | 113 | Forms from Mandsaur awaited
11 | Maharashtra | 14 | 14 | 0 | 0 | 5638 | 5638 | 1. Survey completed in all 14 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 0 | 5638 | 5629 | 5018 | 3371 |  | 3371
12 | Punjab | 4 | 4 | 0 | 0 | 636 | 142 | 1. Survey Camps yet to be scheduled in Ludhiana. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 91 | 233 | 142 | 138 | 125 |  | 125
13 | Rajasthan | 20 | 20 | 0 | 0 | 7381 | 2590 | 1. Survey completed in all 20 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Distt. Coordinator not involved in survey by Jaipur Municipal Corporation. | 338 | 2928 | 2531 | 2444 | 1630 | 61 | 1569 | Bharatpur, Bhilwara, Bundi, Baran, Dausa, Karauli and Pratapgarh Forms received.
14 | Tamil Nadu | 6 | 6 | 0 | 0 | 1433 | 62 | Survey completed in all 6 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 363 | 425 | 58 | 40 | 34 |  | 34 | Forms received from Chennai Kanyakumari. Forms from Madurai awaited
15 | Telangana | 2 | 2 | 0 | 0 | 288 | 0 | No detail of Survey camps scheduled so far involving Distt. Coordinators. | 0 | 0 | 0 |  |  |  | 0 | No MS identified in State
16 | Uttar Pradesh | 47 | 47 | 0 | 0 | 18913 | 7052 | 1. Survey camps yet to be scheduled in districts Banda, Barabanki, Hamirpur, Jaunpur and Kaushambi. 2. Survey partly scheduled in Lucknow, Meerut, Muzafarnagar and Saharanpur in urban areas only. 3. Survey reports alongwith survey forms yet to be received from all the districts. 4. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 11360 | 18412 | 6881 | 6362 | 4497 | 41 | 4456
17 | Uttarakhand | 4 | 4 | 0 | 0 | 3084 | 2531 | Survey reports alongwith survey forms yet to be received from all the districts. | 137 | 2668 | 2517 | 2287 | 1755 |  | 1755
18 | West Bengal | 6 | 6 | 0 | 0 | 1329 | 637 | No Survey camps scheduled so far. | 104 | 741 | 637 | 622 | 555 |  | 555
19 | Chhattisgarh | 0 | 0 | 0 | 0 | 0 | 0 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
20 | Odisha | 0 | 0 | 0 | 0 | 0 | 0 |  | 237 | 237 | 0 | 0 | 0 | 0 | 0
| Total | 170 | 163 | 0 | 7 | 55190 | 25276 | 0 | 13770 | 39046 | 24276 | 21536 | 14612 | 108 | 14504

## Nov 18
Statewise status of Survey of Manual Scavengers as on 28.11.18
S.No. | State | Districts Identified for Survey | Where Survey Camps completed | Where Survey camps underway | Where Survey camps not scheduled | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of MS Identified before this Survey | Total No. of MS Identified in both Surveys | No. of Survey Forms received | No. of forms digitised | No. of MS OTCA |  |  | Remarks
[13 empty] | Released | Rejected | Confirmed
1 | Andhra Pradesh | 5 | 5 | 0 | 0 | 1763 | 1721 | 1. Camp not Scheduled in Anantpur Distt. 2. Distt. Coordinators not involved in survey except in Krishna Distt. 3. Survey Reports alongwith minutes and completed survey forms not received from Districts except minutes received from Krishna Distt. | 78 | 1799 | 1721 | 1547 | 1333 |  | 1333 | Anantpur & Krishna Distt. Forms received
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 1. Survey Report with minutes received from Distt. Golaghat. Survey forms yet to be received. 2. Survey reports and forms yet to be received from other two districts viz. Jorhat and Lakhimpur. | 154 | 696 | 542 | 542 | 510 | 1 | 509
3 | Bihar | 16 | 16 | 0 | 0 | 846 | 0 | 1. Survey camps yet to be scheduled in Araria, Aurangabad, Baxur, Gopalganj, Jahanabad, Katihar, Nalanda, Rohtas, Saharsa and Supaul 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 137 | 137 |  |  |  |  | 0 | Araria Distt. Report received.
4 | Gujarat | 4 | 4 | 0 | 0 | 291 | 108 | 1. Survey report with 126 forms received from Ahmedabad and Rajkot Distts. Minutes of the Survey Camps not received. Survey forms are not signed by Nodal Oficer and Distt. Coordinators and not filled fully. 2. For Surendra Nagar Only Survey Report of identication of 20 MS received. No minutes or survey forms received. 3. In Distt. Anand no MS identified. 4. Distts. Anand and Surendra Nagar were added in the list of survey districts at the request of SKA. Perhaps Distt. Coord. were not actively involved in the survey in these districts. | 0 | 108 | 108 | 109 | 93 |  | 93
5 | Haryana | 5 | 5 | 0 | 0 | 1221 | 0 | 1. Information about holding of survey camp in Karnal not received. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 0 | 0 | 0 |  |  |  | 0 | No MS identified in State. State Govt. requested to review.
6 | J & K | 7 | 0 | 0 | 7 |  |  | No Survey camps scheduled so far. | 0 | 0 |  |  |  |  | 0
7 | Jharkhand | 3 | 3 | 0 | 0 | 246 | 201 | No Survey camps scheduled so far. | 0 | 201 | 201 | 131 | 108 |  | 108
8 | Karnataka | 6 | 6 | 0 | 0 | 1793 | 1744 | No Survey camps scheduled so far. | 732 | 2476 | 1719 | 1197 |  |  | 0
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 1. Complete Survey Reports and forms duly translated in English received from Ernakulam and Pallakad Districts. 2. Alapuza Distt. Sent only minutes of the survey camps. | 0 | 600 | 598 | 542 | 488 | 5 | 483
10 | Madhya Pradesh | 14 | 14 | 0 | 0 | 8275 | 1447 | 1. Survey camps yet to be scheduled in Anupur, Ashoknagar, Katni, Narsingpur, Panna and Satna. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 36 | 1483 | 992 | 564 | 113 |  | 113 | Forms from Mandsaur awaited
11 | Maharashtra | 14 | 14 | 0 | 0 | 5638 | 5638 | 1. Survey completed in all 14 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 0 | 5638 | 5629 | 5018 | 2878 |  | 2878
12 | Punjab | 4 | 4 | 0 | 0 | 636 | 142 | 1. Survey Camps yet to be scheduled in Ludhiana. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 91 | 233 | 142 | 138 | 125 |  | 125
13 | Rajasthan | 20 | 20 | 0 | 0 | 7381 | 2590 | 1. Survey completed in all 20 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Distt. Coordinator not involved in survey by Jaipur Municipal Corporation. | 338 | 2928 | 2531 | 1983 | 1140 | 61 | 1079 | Bharatpur, Bhilwara, Bundi, Baran, Dausa, Karauli and Pratapgarh Forms received.
14 | Tamil Nadu | 6 | 6 | 0 | 0 | 1433 | 62 | Survey completed in all 6 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 363 | 425 | 58 | 40 | 34 |  | 34 | Forms received from Chennai Kanyakumari. Forms from Madurai awaited
15 | Telangana | 2 | 2 | 0 | 0 | 288 | 0 | No detail of Survey camps scheduled so far involving Distt. Coordinators. | 0 | 0 | 0 |  |  |  | 0 | No MS identified in State
16 | Uttar Pradesh | 47 | 47 | 0 | 0 | 18913 | 7052 | 1. Survey camps yet to be scheduled in districts Banda, Barabanki, Hamirpur, Jaunpur and Kaushambi. 2. Survey partly scheduled in Lucknow, Meerut, Muzafarnagar and Saharanpur in urban areas only. 3. Survey reports alongwith survey forms yet to be received from all the districts. 4. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 11360 | 18412 | 6881 | 5587 | 3033 | 41 | 2992
17 | Uttarakhand | 4 | 4 | 0 | 0 | 3084 | 2531 | Survey reports alongwith survey forms yet to be received from all the districts. | 137 | 2668 | 2517 |  |  |  | 0
18 | West Bengal | 6 | 6 | 0 | 0 | 1329 | 637 | No Survey camps scheduled so far. | 104 | 741 | 637 | 624 | 555 |  | 555
19 | Chhattisgarh | 0 | 0 | 0 | 0 | 0 | 0 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
20 | Odisha | 0 | 0 | 0 | 0 | 0 | 0 |  | 237 | 237 | 0 | 0 | 0 | 0 | 0
| Total | 170 | 163 | 0 | 7 | 54929 | 25015 | 0 | 13770 | 38785 | 24276 | 18022 | 10410 | 108 | 10302

## Oct. 18
Statewise status of Survey of Manual Scavengers as on 31.10.2018
S.No. | State | Districts Identified for Survey | Where Survey Camps completed | Where Survey camps underway | Where Survey camps not scheduled | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of MS Identified before this Survey | Total No. of MS Identified in both Surveys | No. of Survey Forms received | No. of forms digitised | No. of MS OTCA |  |  | Remarks
[13 empty] | Released | Rejected | Confirmed
1 | Andhra Pradesh | 5 | 5 | 0 | 0 | 1763 | 1721 | 1. Camp not Scheduled in Anantpur Distt. 2. Distt. Coordinators not involved in survey except in Krishna Distt. 3. Survey Reports alongwith minutes and completed survey forms not received from Districts except minutes received from Krishna Distt. | 78 | 1799 | 267 | 1283 | 1095 |  | 1095 | Anantpur & Krishna Distt. Forms received
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 1. Survey Report with minutes received from Distt. Golaghat. Survey forms yet to be received. 2. Survey reports and forms yet to be received from other two districts viz. Jorhat and Lakhimpur. | 154 | 696 | 542 | 542 | 510 | 1 | 509
3 | Bihar | 16 | 16 | 0 | 0 | 846 | 0 | 1. Survey camps yet to be scheduled in Araria, Aurangabad, Baxur, Gopalganj, Jahanabad, Katihar, Nalanda, Rohtas, Saharsa and Supaul 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 137 | 137 |  |  |  |  | 0 | Araria Distt. Report received.
4 | Gujarat | 4 | 4 | 0 | 0 | 291 | 108 | 1. Survey report with 126 forms received from Ahmedabad and Rajkot Distts. Minutes of the Survey Camps not received. Survey forms are not signed by Nodal Oficer and Distt. Coordinators and not filled fully. 2. For Surendra Nagar Only Survey Report of identication of 20 MS received. No minutes or survey forms received. 3. In Distt. Anand no MS identified. 4. Distts. Anand and Surendra Nagar were added in the list of survey districts at the request of SKA. Perhaps Distt. Coord. were not actively involved in the survey in these districts. | 0 | 108 | 108 | 109 | 93 |  | 93
5 | Haryana | 5 | 5 | 0 | 0 | 1221 | 0 | 1. Information about holding of survey camp in Karnal not received. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 0 | 0 | 0 |  |  |  | 0 | No MS identified in State. State Govt. requested to review.
6 | J & K | 7 | 0 | 0 | 7 |  |  | No Survey camps scheduled so far. | 0 | 0 |  |  |  |  | 0
7 | Jharkhand | 3 | 3 | 0 | 0 | 246 | 201 | No Survey camps scheduled so far. | 0 | 201 | 201 | 94 | 77 |  | 77 | Forms received from Lohardaga
8 | Karnataka | 6 | 6 | 0 | 0 | 1793 | 1744 | No Survey camps scheduled so far. | 732 | 2476 | 1719 | 1019 |  |  | 0
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 1. Complete Survey Reports and forms duly translated in English received from Ernakulam and Pallakad Districts. 2. Alapuza Distt. Sent only minutes of the survey camps. | 0 | 600 | 598 | 542 | 488 | 5 | 483
10 | Madhya Pradesh | 14 | 14 | 0 | 0 | 8275 | 1447 | 1. Survey camps yet to be scheduled in Anupur, Ashoknagar, Katni, Narsingpur, Panna and Satna. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 36 | 1483 | 992 | 564 | 113 |  | 113 | Forms from Mandsaur awaited
11 | Maharashtra | 14 | 14 | 0 | 0 | 5638 | 5638 | 1. Survey completed in all 14 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 0 | 5638 | 5629 | 4148 | 2535 |  | 2535
12 | Punjab | 4 | 4 | 0 | 0 | 636 | 142 | 1. Survey Camps yet to be scheduled in Ludhiana. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 91 | 233 | 142 | 138 | 125 |  | 125 | MS Identified in Ludhiana, Sangrur and Fatehgarh Sahib.
13 | Rajasthan | 20 | 20 | 0 | 0 | 7381 | 2121 | 1. Survey completed in all 20 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Distt. Coordinator not involved in survey by Jaipur Municipal Corporation. | 338 | 2459 | 2062 | 1983 | 1140 | 61 | 1079 | Bharatpur, Bhilwara, Bundi, Baran, Dausa, Karauli and Pratapgarh Forms received.
14 | Tamil Nadu | 6 | 6 | 0 | 0 | 1433 | 62 | Survey completed in all 6 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 363 | 425 | 58 | 40 | 34 |  | 34 | Forms received from Chennai Kanyakumari. Forms from Madurai awaited
15 | Telangana | 2 | 2 | 0 | 0 | 288 | 0 | No detail of Survey camps scheduled so far involving Distt. Coordinators. | 0 | 0 | 0 |  |  |  | 0 | No MS identified in State
16 | Uttar Pradesh | 47 | 47 | 0 | 0 | 16661 | 6126 | 1. Survey camps yet to be scheduled in districts Banda, Barabanki, Hamirpur, Jaunpur and Kaushambi. 2. Survey partly scheduled in Lucknow, Meerut, Muzafarnagar and Saharanpur in urban areas only. 3. Survey reports alongwith survey forms yet to be received from all the districts. 4. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 11360 | 17486 | 5955 | 3105 | 2228 | 41 | 2187
17 | Uttarakhand | 4 | 4 | 0 | 0 | 3084 | 2531 | Survey reports alongwith survey forms yet to be received from all the districts. | 137 | 2668 |  |  |  |  | 0
18 | West Bengal | 6 | 6 | 0 | 0 | 1329 | 637 | No Survey camps scheduled so far. | 104 | 741 | 637 |  |  |  | 0
19 | Chhattisgarh | 0 | 0 | 0 | 0 | 0 | 0 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
20 | Odisha | 0 | 0 | 0 | 0 | 0 | 0 |  | 237 | 237 | 0 | 0 | 0 | 0 | 0
| Total | 170 | 163 | 0 | 7 | 52677 | 23620 | 0 | 13770 | 37390 | 18910 | 13567 | 8438 | 108 | 8330

## Aug 18
Statewise status of Survey of Manual Scavengers as on 31.8.2018
S.No. | State | Districts Identified for Survey | Where Survey Camps completed | Where Survey camps underway | Where Survey camps not scheduled | No. of persons registered | No. of MS Reported Identified by State | Remarks | No. of MS Identified before this Survey | Total No. of MS Identified in both Surveys | No. of Survey Forms received | No. of forms digitised | No. of MS OTCA |  |  | Remarks
[13 empty] | Released | Rejected | Confirmed
1 | Andhra Pradesh | 5 | 5 | 0 | 0 | 1763 | 1721 | 1. Camp not Scheduled in Anantpur Distt. 2. Distt. Coordinators not involved in survey except in Krishna Distt. 3. Survey Reports alongwith minutes and completed survey forms not received from Districts except minutes received from Krishna Distt. | 78 | 1799 | 267 | 249 |  |  | 0 | Anantpur & Krishna Distt. Forms received
2 | Assam | 3 | 3 | 0 | 0 | 876 | 542 | 1. Survey Report with minutes received from Distt. Golaghat. Survey forms yet to be received. 2. Survey reports and forms yet to be received from other two districts viz. Jorhat and Lakhimpur. | 154 | 696 | 542 | 542 | 510 | 1 | 509
3 | Bihar | 16 | 16 | 0 | 0 | 846 | 0 | 1. Survey camps yet to be scheduled in Araria, Aurangabad, Baxur, Gopalganj, Jahanabad, Katihar, Nalanda, Rohtas, Saharsa and Supaul 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 137 | 137 |  |  |  |  | 0 | Araria Distt. Report received.
4 | Gujarat | 4 | 4 | 0 | 0 | 291 | 108 | 1. Survey report with 126 forms received from Ahmedabad and Rajkot Distts. Minutes of the Survey Camps not received. Survey forms are not signed by Nodal Oficer and Distt. Coordinators and not filled fully. 2. For Surendra Nagar Only Survey Report of identication of 20 MS received. No minutes or survey forms received. 3. In Distt. Anand no MS identified. 4. Distts. Anand and Surendra Nagar were added in the list of survey districts at the request of SKA. Perhaps Distt. Coord. were not actively involved in the survey in these districts. | 0 | 108 | 108 | 105 | 93 |  | 93
5 | Haryana | 5 | 5 | 0 | 0 | 1221 | 0 | 1. Information about holding of survey camp in Karnal not received. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 0 | 0 | 0 |  |  |  | 0 | No MS identified in State. State Govt. requested to review.
6 | J & K | 7 | 0 | 0 | 7 |  |  | No Survey camps scheduled so far. | 0 | 0 |  |  |  |  | 0
7 | Jharkhand | 3 | 3 | 0 | 0 | 159 | 159 | No Survey camps scheduled so far. | 0 | 159 | 159 | 94 | 77 |  | 77 | Forms received from Lohardaga
8 | Karnataka | 6 | 6 | 0 | 0 | 1793 | 1744 | No Survey camps scheduled so far. | 732 | 2476 | 1226 |  |  |  | 0 | Forms received from Mysoru
9 | Kerala | 4 | 4 | 0 | 0 | 916 | 600 | 1. Complete Survey Reports and forms duly translated in English received from Ernakulam and Pallakad Districts. 2. Alapuza Distt. Sent only minutes of the survey camps. | 0 | 600 | 592 | 542 | 488 | 5 | 483
10 | Madhya Pradesh | 14 | 14 | 0 | 0 | 8275 | 1447 | 1. Survey camps yet to be scheduled in Anupur, Ashoknagar, Katni, Narsingpur, Panna and Satna. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 36 | 1483 | 992 | 567 |  |  | 0 | Forms from Mandsaur awaited
11 | Maharashtra | 14 | 14 | 0 | 0 | 5647 | 5269 | 1. Survey completed in all 14 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 0 | 5269 | 5260 | 3045 |  |  | 0 | Forms from Amravati Awaited
12 | Punjab | 4 | 3 | 1 | 0 | 636 | 142 | 1. Survey Camps yet to be scheduled in Ludhiana. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 91 | 233 | 142 | 138 | 125 |  | 125 | MS Identified in Ludhiana, Sangrur and Fatehgarh Sahib.
13 | Rajasthan | 20 | 20 | 0 | 0 | 7237 | 2039 | 1. Survey completed in all 20 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Distt. Coordinator not involved in survey by Jaipur Municipal Corporation. | 338 | 2377 | 1608 | 1294 | 1078 |  | 1078 | Bharatpur, Bhilwara, Bundi, Baran, Dausa and Pratapgarh Forms received. Forms from Karauli awaited.
14 | Tamil Nadu | 6 | 6 | 0 | 0 | 1433 | 62 | Survey completed in all 6 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 363 | 425 | 58 | 40 |  |  | 0 | Forms received from Chennai Kanyakumari. Forms from Madurai awaited
15 | Telangana | 2 | 2 | 0 | 0 | 288 | 0 | No detail of Survey camps scheduled so far involving Distt. Coordinators. | 0 | 0 | 0 |  |  |  | 0 | No MS identified in State
16 | Uttar Pradesh | 47 | 41 | 6 | 0 | 16661 | 6126 | 1. Survey camps yet to be scheduled in districts Banda, Barabanki, Hamirpur, Jaunpur and Kaushambi. 2. Survey partly scheduled in Lucknow, Meerut, Muzafarnagar and Saharanpur in urban areas only. 3. Survey reports alongwith survey forms yet to be received from all the districts. 4. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 11360 | 17486 | 5955 | 2501 | 970 |  | 970
17 | Uttarakhand | 4 | 4 | 0 | 0 | 1263 |  | Survey reports alongwith survey forms yet to be received from all the districts. | 137 | 137 |  |  |  |  | 0
18 | West Bengal | 6 | 6 | 0 | 0 | 1275 | 66 | No Survey camps scheduled so far. | 104 | 170 |  |  |  |  | 0
19 | Chhattisgarh | 0 | 0 | 0 | 0 | 0 | 0 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0
20 | Odisha | 0 | 0 | 0 | 0 | 0 | 0 |  | 237 | 237 | 0 | 0 | 0 | 0 | 0
| Total | 170 | 156 | 7 | 7 | 50580 | 20025 | 0 | 13770 | 33795 | 16909 | 9117 | 3341 | 6 | 3335

## 31.7.18
Statewise status of Survey of Manual Scavengers as on 31.7.2018
S.No. | State | No. of MS Identified before this Survey | Districts Identified for Survey | Where Survey Camps completed | Where Survey camps underway | Where Survey camps not scheduled | No. of persons registered | No. of MS Reported Identified reported by State | Remarks | No. of Complete Survey Forms with minutes and Distt. Reports received | No. of forms digitised | No. of MS OTCA |  |  | Remarks
[12 empty] | Released | Rejected | Confirmed
1 | Andhra Pradesh | 78 | 5 | 5 | 0 | 0 | 903 | 734 | 1. Camp not Scheduled in Anantpur Distt. 2. Distt. Coordinators not involved in survey except in Krishna Distt. 3. Survey Reports alongwith minutes and completed survey forms not received from Districts except minutes received from Krishna Distt. | 267 | 248 |  |  |  | Krishna Distt. Forms received
2 | Assam | 154 | 3 | 3 | 0 | 0 | 876 | 542 | 1. Survey Report with minutes received from Distt. Golaghat. Survey forms yet to be received. 2. Survey reports and forms yet to be received from other two districts viz. Jorhat and Lakhimpur. | 542 | 542 | 510 | 17 |  | Golaghat (196), Jorhat (197), Lakhimpur (149)
3 | Bihar | 137 | 16 | 16 | 0 | 0 |  |  | 1. Survey camps yet to be scheduled in Araria, Aurangabad, Baxur, Gopalganj, Jahanabad, Katihar, Nalanda, Rohtas, Saharsa and Supaul 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately.
4 | Gujarat | 0 | 4 | 4 | 0 | 0 | 146 | 146 | 1. Survey report with 126 forms received from Ahmedabad and Rajkot Distts. Minutes of the Survey Camps not received. Survey forms are not signed by Nodal Oficer and Distt. Coordinators and not filled fully. 2. For Surendra Nagar Only Survey Report of identication of 20 MS received. No minutes or survey forms received. 3. In Distt. Anand no MS identified. 4. Distts. Anand and Surendra Nagar were added in the list of survey districts at the request of SKA. Perhaps Distt. Coord. were not actively involved in the survey in these districts. | 108 | 100
5 | Haryana | 0 | 5 | 5 | 0 | 0 | 1040 | 0 | 1. Information about holding of survey camp in Karnal not received. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 0
6 | J & K | 0 | 7 | 0 | 0 | 7 |  |  | No Survey camps scheduled so far.
7 | Jharkhand | 0 | 3 | 3 | 0 | 0 | 159 | 159 | No Survey camps scheduled so far. | 159 |  |  |  |  | Forms received from Lohardaga
8 | Karnataka | 732 | 6 | 6 | 0 | 0 |  |  | No Survey camps scheduled so far.
9 | Kerala | 0 | 4 | 4 | 0 | 0 | 916 | 600 | 1. Complete Survey Reports and forms duly translated in English received from Ernakulam and Pallakad Districts. 2. Alapuza Distt. Sent only minutes of the survey camps. | 592 | 542 | 488 | 21 |  | 8 Forms of Distt. Ernakulam pending. 50 forms found incorrect/incomplete
10 | Madhya Pradesh | 36 | 14 | 14 | 0 | 0 | 8016 | 1067 | 1. Survey camps yet to be scheduled in Anupur, Ashoknagar, Katni, Narsingpur, Panna and Satna. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 1067 | 130 |  |  |  | Forms of Distts.Guna, Narsinhpur, Katni, Damoh and Chhatarpur received.
11 | Maharashtra | 0 | 14 | 14 | 0 | 0 | 5647 | 5647 | 1. Survey completed in all 14 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 5647 | 470
12 | Punjab | 91 | 4 | 3 | 0 | 1 | 144 | 142 | 1. Survey Camps yet to be scheduled in Ludhiana. 2. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 142 |  |  |  |  | Survey completedin Ludhiana, Sangrur and Fatehgarh Sahib. In Jalandhar dates to be finalised.
13 | Rajasthan | 338 | 20 | 20 | 0 | 0 | 7053 | 1602 | 1. Survey completed in all 20 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. 2. Distt. Coordinator not involved in survey by Jaipur Municipal Corporation. | 1356 | 1213 | 1078 |  |  | Bhilwara, Bundi, Baran, Dausa and Pratapgarh Forms received
14 | Tamil Nadu | 363 | 6 | 6 | 0 | 0 | 885 | 18 | Survey completed in all 6 districts. No survey report received so far. Survey reports alongwith minutes and completed survey forms of the districts completing the survey be sent immediately. | 18 |  |  |  |  | Forms received from Chennai.
15 | Telangana | 0 | 2 | 2 | 0 | 0 | 288 | 0 | No detail of Survey camps scheduled so far involving Distt. Coordinators. | 0
16 | Uttar Pradesh | 11230 | 47 | 40 | 4 | 3 | 28796 | 4670 | 1. Survey camps yet to be scheduled in districts Banda, Barabanki, Hamirpur, Jaunpur and Kaushambi. 2. Survey partly scheduled in Lucknow, Meerut, Muzafarnagar and Saharanpur in urban areas only. 3. Survey reports alongwith survey forms yet to be received from all the districts. 4. Reports of undue delay in the process of house to house verification. This work needs to be completed in a time bound manner say within 10 days of completion of survey camp. | 3614 | 1860 | 970 |  |  | 825 MS identified in Kasganj and 231 in Etawa, 2965 forms of Amroha and 649 of Jalaun received
17 | Uttarakhand | 137 | 4 | 4 | 0 | 0 | 1263 |  | Survey reports alongwith survey forms yet to be received from all the districts.
18 | West Bengal | 104 | 6 | 6 | 0 | 0 |  |  | No Survey camps scheduled so far.
| Total | 13400 | 170 | 155 | 4 | 11 | 56132 | 15327 | 0 | 13512 | 5105 | 3046 | 38